## Sheet1
HPY Code | ATMID-1stATM | Call Received Date | Bank Name | ATM Location | City | State | Installation status | Installation & ETA. | Technician | Remark
Axis1130202101 | CPRH02004 | 2021-11-16 | Axis | Shop No. 3A, "Pritam Apartments", Sher-E-Punjab C.H.S. Ltd., Mahakali Caves Road, Andheri (E), Mumbai - 400 093 | Mumbai | MAHARASHTRA | Completed | 2021-11-23 | Rahul Dubey | As per update from team installation done same updated to HPY on mail with snaps 23-11-2021
Axis1130202102 | CPRH45402 | 2021-11-16 | Axis | NALASOPARA BR.- 1 ( Sri pal plaza) , Mumbai S1AN454 | Mumbai | MAHARASHTRA | Completed | 2021-11-24 | Rahul Dubey | camera has been installed & same updated to HPY on mail with snaps 24-11-2021
Axis1130202103 | SPCN6531 | 2021-11-16 | Axis | Willingdon Sports Club, Infront of Institute of Engineering College, Mahalaxmi-Hajiali Road, Mahalaxmi, Mumbai-400 034 | Mumbai | MAHARASHTRA | Completed | 2021-11-18 | Rahul Dubey | camera has been installed & same updated to HPY on mail with snaps 18-11-2021
Axis1130202104 | TPCN156435 | 2021-11-16 | Axis | Radhakrishana Apartment, C-3. Shop No.6, Sector-9, Airoli, Navi Mumbai, Maharashtra – 400708. | Mumbai | MAHARASHTRA | Completed | 2021-11-22 | Rahul Dubey | camera has been installed & same updated to HPY on mail with snaps 22-11-2021
Axis1130202106 | APCN57206 | 2021-11-16 | Axis | New fashion hair art Sarswati chawal kranti nagar ambedkar chowk Kandivali east mumbai 400101 | Mumbai | MAHARASHTRA | Completed | 2021-11-23 | Rahul Dubey | As per update from team installation done same updated to HPY on mail with snaps 23-11-2021
Axis1130202107 | BPCN254405 | 2021-11-16 | Axis | Shop 251, Govind Nagar, Opp Himalay Society, Asalpha, Ghatkopar(West)-400084 | Mumbai | MAHARASHTRA | Completed | 2021-11-19 | Rahul Dubey | Camera has been installed & same updated to HPY on mail with snaps 20-11-2021
Axis1130202108 | BPCN206410 | 2021-11-16 | Axis | Shop No. 41, Bellow chembur Monorail stn. Rationig Office, R.C. Marg, near Fine art Hall, Chembur mumbai-400071 | Mumbai | MAHARASHTRA | Completed | 2021-11-20 | Rahul Dubey | Camera has been installed & same updated to HPY on mail with snaps 20-11-2021
Axis1130202109 | APCN77113 | 2021-11-16 | Axis | Shop no.16, Matoshri nagar, Gaondevi, Vimco naka, Ambernath (w).421505 | Mumbai | MAHARASHTRA | Completed | 2021-11-22 | Rahul Dubey | camera has been installed & same updated to HPY on mail with snaps 22-11-2021
Axis1130202110 | BPCN156425 | 2021-11-16 | Axis | Shop 812 Patel Niwas Midc Rd Yadav Nagar Airoli 400708, Maharashtra | Mumbai | MAHARASHTRA | Completed | 2021-11-22 | Rahul Dubey | camera has been installed & same updated to HPY on mail with snaps 22-11-2021
Axis1130202111 | BPCN162024 | 2021-11-16 | Axis | Shop.752, Phool Niwas Guru Nanak Nagar, Guru Govind Road, Ghatkopar West, Mumbai 400086, Maharashtra | Mumbai | MAHARASHTRA | Completed | 2021-11-19 | Rahul dubey | Camera has been installed & same updated to HPY on mail with snaps 20-11-2021
Axis1130202112 | BPCN162025 | 2021-11-16 | Axis | shop -2 badal house vv rd. ambedkar chowk kurla w-400070 | Mumbai | MAHARASHTRA | Completed | 2021-11-20 | Rahul Dubey | Camera has been installed & same updated to HPY on mail with snaps 20-11-2021
Axis1130202113 | BPCN206415 | 2021-11-16 | Axis | 3/305/3815 shop -6 tagore nagar vikroli e - 400083 | Mumbai | MAHARASHTRA | Completed | 2021-11-20 | Rahul Dubey | Camera has been installed & same updated to HPY on mail with snaps 20-11-2021
Axis1130202114 | BPCN247324 | 2021-11-16 | Axis | Shop no2364, Rukiya transport, Gavanpada, R C marg, Chembur | Mumbai | MAHARASHTRA | Completed | 2021-11-20 | Rahul Dubey | Camera has been installed & same updated to HPY on mail with snaps 20-11-2021
Axis1130202115 | APCN46508 | 2021-11-16 | Axis | Shop no.5,pakeeza market, m s Ali road, opposite royal cinema,grant road East,mumbai-400008 | Mumbai | MAHARASHTRA | Completed | 2021-11-18 | Rahul Dubey | camera has been installed & same updated to HPY on mail with snaps 18-11-2021
201356131 | MCRM3387 | 2021-11-20 | Money spot | Takai - Adoshi Road, Dheku, Khopoli Maharashtra 410203 | DHEKU | MAHARASHTRA | Completed | 2021-12-01 | Rahul Dubey | 01-12-2021 As per technician Rahul dubey on what'sapp with snaps installation done same updated to HPY on mail by tracker
201351810 | MCRM3919 | 2021-11-20 | Money spot | Shop No. 6, Chandra Apt., Rashmi Nagar, Ram Mandir Road, Near Old Viva College 401303 | VIRAR | MAHARASHTRA | Completed | 2021-11-29 | Rahul Dubey | 29-11-2021 As per technician Rahul dubey on what'sapp with snaps installation done same updated to HPY on mail with images